## Intro
Note: Mock data currently within risk register is for example purposes; it should be deleted before using
MHK risk register template, version: September 23, 2015
Project Name and Overview
Igiugig Village Council (IVC) DE-EE0007348 Next Generation MHK River Power System, Optimized for Performance, Durability, and Survivability
Risk Register Template Introduction:
This risk register template is a companion to the MHK Technology Development Risk Management Framework document. The terminology used in this template is further defined within the framework document. The purpose of this risk register template is to be a tool for identifying risks, analyzing risks, and planning risk responses. As appropriate, this template should be customized by the user to improve its use for their application. The user should add/modify valid data options with the "valid data fields" worksheet by following the procedure on that worksheet (e.g., risk owners "owner" must be modified for each project). Row 3 of the risk "Risk Register" worksheet provides filter options for viewing risk register data; the data can be filtered and reordered using these filter options.
Link to MHK Technology Development Risk Management Framework report

## Risk Register
IDENTIFY RISKS PROCESS | [7 empty] | ANALYZE RISKS PROCESS | [5 empty] | RISK RESPONSE PROCESS--STRATEGY & TIMING |  |  | RISK RESPONSE PROCESS--RESIDUAL RISK | [5 empty] | CONTINGENCY PLAN
| RBS |  |  |  |  | Technology Life Phase | Risk Owner | Baseline Risk (before response) | [5 empty] | Risk Response |  |  | Residual Risk (after response) | [5 empty] | Contingency Plan (as if the risk has occurred)
Revision Date | RBS Level 1 | RBS Level 2 | Risk Name | TRL | TPL |  |  | + - | TYP | SEV | FRQ | RPN | Description (with assumptions) | Strategy | Description (with assumptions); incude Timing and Triggers | Response Timing | SEV | FRQ | RPN | Description (with assumptions) | Secondary Risks Resulting From Risk Response | Recommendations & Action Items
Budget Period 1
2017-02-21 | External | 4.6 Regulatory | task 2.2 Smolt probability of encounter model - data sharing | 7 | 7 | NA | N. Johnson (environmental) | - | E | 2 | 4 | 8 | Data sharing from BBSRI at risk | mitigate | facilitate conversations with Umaine on data sharing | now | 1 | 3 | 3 | If data is not shared move on to next step of conceptual monitoring plan development | NA | N. Johnson to continue to faciliate conversations between LGL BBSRI and Umaine re: data sharing | continue environmental monitoring plan development without probability of encounter model
2017-02-21 | External | 4.9 External stakeholder | Task 5 Ice data collected | 7 | 7 | NA | J. Kasper (UAA lead) | - | E | 3 | 3 |  | Ice data collection unsuccessful | mitigate | real time data collection implemented | now | 2 | 1 | 2 | If real time data collection is not successful equipment retrieved and redeployed in May 2017 | Increased complexity | UAF to take lead on techical side, M. Worthington to continue to manage this effort | Redesign Ice study equipment for oper water testing, evaluate needs for ice data for component validation
Budget Period 2
2017-02-21 | External | 4.6 Regulatory | Permitting/Licensing complete for in water testing | 7 | 7 | Multiple (or all) life phases | N. Johnson (environmental) | - | R | 4 | 4 | 16 | Appropriate permits and licenses procured in time for open water testing | avoid | FERC Final license application submittal scheudled for 12/17 | now | 4 | 3 | 12 | FERC License not granted in time | Schedule Slip budget creep | Initiate communication with Regulatory agencies and FERC to scope FERC License. Resource appropriatley for completion by 12/17, respond to Additional Information Requests promptly after submission | Consider operating under Verdant Exemption for first year of operation
2017-02-21 | Technical | 1.5 Technology | Generator Final Design | 7 | 7 | Design | R. Tyler (lead engineer) | - | P | 3 | 4 | 12 | Wet Gap Generator design not yet complete | mitigate | Design reviews and component validation testing | before design finalized | 3 | 2 |  | manufactured product is stil out of specificaiton | increased cost schedule slip | Work closeley with Generator vendor to develop clear specification and ensure genertor design meets this specification | Refurbish and reuse exisitng Generator
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Generator Procurement | 7 | 7 | Assembly and commissioning | R. Tyler (lead engineer) | - | T | 3 | 4 | 12 | Timing of generator procurement from IKM could be tight for schedule | avoid | Ensure Generator delivery by 2/2018 to allow adequate time for testing using project development plan with regular status reports | before manufacturing | 3 | 3 | 9 | Generator has manufacturing or integration issues that need resolution in limited time frame | increased effort and cost | Continue Communication with IKM and ORPC Ireland to ensure timely procurement | Refurbish and reuse exisitng Generator
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Buoyancy System Procurement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 2 | 2 | 4 | components are not available | avoid | Compile BOM and ascertain component lead times from vendors in advance of PO issue | before PO issued | 3 | 1 | 3 | Unexepcted component shortage | NA | USE COTS components | delay buoyancy system validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Structural Assembly Procurement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 3 | 3 | 9 | Fabricated components have significant lead times | mitigate | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | before PO issued | 3 | 2 | 6 | Unexpected fabrication delays | Increased cost and effort | Freqent vendor communications, contract includes penalties for late delivery | Delay full system validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Turbine Procuement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 3 | 4 | 12 | Fabricated components have significant lead times | mitigate | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | before PO issued | 3 | 2 | 6 | Unexpected fabrication delays | Increased cost and effort | Freqent vendor communications, contract includes penalties for late delivery | Delay full system validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Power Electronics Procurement | 7 | 7 | Multiple (or all) life phases | M. Worthington (Project Management) | - | T | 3 | 4 | 12 | Singel source vendor for some components that require design completion and fabrication | mitigate | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | now | 3 | 3 | 9 | Unexpected design/fabrication FAT delays | Increased cost and effort | Freqent vendor communications, contract includes penalties for late delivery | Delay laboratory validation
2017-02-21 | Commercial | 3.3 Suppliers and vendors | SCADA Procurement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 3 | 4 | 12 | components are not available, integration of components and software is delayed | avoid | Compile BOM and ascertain component lead times from vendors in advance of PO issue | before PO issued | 3 | 3 | 9 | Unexepcted component shortage, personel shortage for SCADA development | NA | USE COTS components, Start ACADA development early | delay SCADA system validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | power and Data cable procurement | 7 | 7 | Multiple (or all) life phases | M. Worthington (Project Management) | - | T | 3 | 4 | 12 | Fabrication delays and out of spec delivered product | mitigate | Compile BOM and ascertain component lead times from vendors in advance of PO issue | before PO issued | 3 | 3 |  | Unexepcted component shortage | NA | USE COTS components where possible | delay Power and data cable validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Mooring Sytem Procurement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 3 | 3 | 9 | components are not available | avoid | Compile BOM and ascertain component lead times from vendors in advance of PO issue | before PO issued | 3 | 1 | 3 | Unexepcted component shortage | NA | USE COTS components | delay moorins system validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Dirveline Procurement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 3 | 4 | 12 | Custom components require fabrication lead time | mitigate | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | before PO issued | 3 | 2 | 6 | Unexpected fabrication delays | Increased cost and effort | Freqent vendor communications, contract includes penalties for late delivery | Delay full system validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Mechanical Brake Procurement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 3 | 4 | 12 | Custom components require fabrication lead time | mitigate | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | before PO issued | 3 | 2 | 6 | Unexpected fabrication delays | Increased cost and effort | Freqent vendor communications, contract includes penalties for late delivery | Delay mechanical brake validation tests
2017-02-21 | Commercial | 3.3 Suppliers and vendors | Mechanical Brake Procurement | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | T | 3 | 4 | 12 | Custom components require fabrication lead time | mitigate | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | before PO issued | 3 | 2 | 6 | Unexpected fabrication delays | Increased cost and effort | Freqent vendor communications, contract includes penalties for late delivery | Delay mechanical brake validation tests
2017-02-21 | Technical | 1.5 Technology | Buoyancy System Validation | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | Q | 4 | 3 | 12 | Buoyancy System fails some or all of validation tests | avoid | Utilizing Incremetnal improvements to a proven concept, add redundancy to design Perform land based tests in May 2017 and move on to on water validation tests prior to shipment to Igiugig | before assembly and commissioning | 3 | 2 | 6 | Unexpected component failure after validation but prior to deployment | Increased cost and effort | Clearly scope validation tests to ensure tests rigoroulsy validatebuoyncy system | Secondary redundant isolated recovery system also validated
2017-02-21 | Technical | 1.5 Technology | Structural Assembly Validation | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | Q | 4 | 3 | 12 | Sturctural Assembly fails some or all of validation tests | avoid | FEA analysis of structure include load factors following DNV standards and considers extreme loading conditions such as uneven bottom and detalied CAD models for subsystem interfaces vlaidation tests to ensure strucutral integrityu meets specs incorporate structural redundancy | before assembly and commissioning | 3 | 2 | 6 | unexpcted structural failure | additional desing work, materials, or strucutral damage during validation could increase cost to repair | Complete thorough design and analysis, desing to DNV standards, incoproate redundant strucutre where possible | Utilize local resources to effect repair and/or structural improvements
2017-02-21 | Technical | 1.5 Technology | Turbine Validation | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | Q | 3 | 3 | 9 | Turbine Assembly fails some or all of validation tests | avoid | Utilize CFD as design tool for performance validation, FEA analysis of turbines include load factors following DNV standards and considers extreme loading conditions, secondary design input from composite manufacturer | before assembly and commissioning | 3 | 2 | 6 | unexpected turbine failure | increased cost added structural elements could reduce turbine performance | thorough design and analysis, utilizing third party expertise to confirm design | accept lower power output, system removal, inspection and turbine replacement if necessary
2017-02-21 | Technical | 1.5 Technology | Generator Validation | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | Q | 3 | 4 | 12 | Genertor fails some or all of validation tests | avoid | Factory Accpetance testing and laboratory testing of Genertor integrated with Power elecrtornics to ensure compatibility | before assembly and commissioning | 3 | 2 | 6 | unexpected generator failure | Increased cost, schedule slip possible | Ensure adequate Factory acceptance testing and laboratory validation before shipment ot Igiugig | Refurbish and reuse protptype generator while effecting generator repair
2017-02-21 | Technical | 1.5 Technology | Power Electronics Validation | 7 | 7 | Multiple (or all) life phases | M. Worthington (Project Management) | - | Q | 3 | 4 | 12 | Power Electronics fails validation | avoid | Factory accpetance tests and sequenced laboratory testing to ensure Power Electronics meets requirements before shipment | before assembly and commissioning | 3 | 3 | 9 | unexpected Power Electonics failure or grid integrid issues | incresed cost, schedule slip possible | Adequate factory acceptance tests, thorough laboratory validation prior to shipment | dissipate power through secondary load bank or brake RivGen device while resolving PE issues , revert to grid following system if needed
2017-02-21 | Technical | 1.5 Technology | SCADA Validation | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) | - | Q | 3 | 4 | 12 | SCADA system fails validation | avoid | Factory accpetance tests and sequenced laboratory testing to ensure SCADA meets requirements before shipment | before assembly and commissioning | 3 | 3 | 9 | unexpected SCADA failure or communciations issues | increased cost | Adequate bench tests through full length power and data cables, laboratory validation prior to shipment | Operate with simplified control system remove device and repair if on device SCADA compromised.
2017-02-21 | Technical | 1.5 Technology | power and Data cable validation | 7 | 7 | Multiple (or all) life phases | M. Worthington (Project Management) | - | Q | 4 | 3 | 12 | Power and data cables failure | avoid | Utilize proven cable technology utilize secondary cable armor in high risk areas utilize redundant conductors for data and fiber optic, reduce inspections and associated wear and tear | before assembly and commissioning | 4 | 2 | 8 | unexpected power and data cable failure | Increased cost and operational complexity, increased uncertainty of cable health with reduced inspections | ensure cable meets specs test full length cable with SCADA system to ensure data signal is adequate | Replace power and data cable
2017-02-21 | Technical | 1.5 Technology | Mooring Sytem Validation | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) |  | Q | 5 | 3 | 15 | Mooring system failure | avoid | Design to DNV standards, utilize geophyisical knowledge and seek industry expertise to specify mooring system components, consider most favorable failure modes | before assembly and commissioning | 5 | 2 | 10 | unexpected mooring system failure | increased size and operational complexity as a result of desing to high load and safety factors | Utilize industry expertise to guide mooring system design | Allow anchor slip as favorable failure mode, replace drage anchors with gravity anchors if needed.
2017-02-21 | Technical | 1.5 Technology | Dirveline Validation | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) |  | Q | 4 | 4 | 16 | Driveline failure | avoid | Throught validation testing, desing system for increased operational tolerances and loads, choosed components with long service life and minimal maintenance and alignement requirements increase modularity for replacement | before assembly and commissioning | 4 | 3 | 12 | unexpected direvline failure | Incresed cost | Complete thorough validation testing and incorpoate design mods as needed | Validation tests in advance of system build, leaving time to redesign and replace.
2017-02-21 | Technical | 1.5 Technology | Mechanical Brake | 7 | 7 | Multiple (or all) life phases | R. Tyler (lead engineer) |  | Q | 4 | 4 | 16 | Mechanical Brake Failure | avoid | Throught validation testing, redundant electrical brake, Rely on third party expertise for design | before assembly and commissioning | 3 | 3 | 9 | unexpected mechanical brake failure | Incresed cost and complexity | Complete thorough validation testing including redudnant electrical brake | use electrical brake or remove system from current
Budget Period 3
2017-02-24 | External | 4.6 Regulatory | Receipt of all permits and licesenses | NA | NA | Multiple (or all) life phases | N. Johnson (environmental) | - | R | 5 | 4 | 20 | Reciept of FERC Pilot license or permits are delayed and compromise deployment | avoid | Continue regular dialogue with regulatory agencies after final pilot license and other permit applications, respond to AIRs in timely manner | December | 5 | 3 | 15 | uncertainity with regurlatory agency approvals in spite of regular communication and timely responses | increased cost and effort | manage personnel time and availablity accordingly | Move forward under Verdant exemption, secure necessary state permits
2017-02-24 | Management | 2.1 Project management | Component delivery to Igiugig | 7 | 7 | Transportation | M. Worthington (Project Management) | - | T | 4 | 3 | 12 | Component shipment to Igiugig is delayed due to schedule slip, transportation contractor issues, weather or other | mitigate | Track project schedule, align component validation and delivery to port of shipment with shipper schedules, ship components early if possible arrival on first barge of season (June 2018) or second (Jluy 2018) at latest | before assembly and commissioning | 4 | 2 | 8 | Unexcepcted or uncontrollabel circumstances lead to delays | increased cost and effort | track shipment continuously | delay deployment to 2019 if component delivery is delayed past July 2018
2017-02-24 | Technical | 1.6 Technical interfaces | Device assmebly | 7 | 7 | Assembly and commissioning | R. Tyler (lead engineer) | - | T | 4 | 3 | 12 | Device assembly difficult or requires modification in Igiugig | mitigate | Device assembly is fdifficult or requires workaround in Igiugig due to component interfaces, component damage during shipment, or other. Timing June-August 2018 | June | 4 | 2 | 8 | Preassembl as many components as possible prior to shipment to Igiugig | Increased cost and effort | include device assembly in validation with as many components as practical avoid unnecsary assembly steps prior to shipment to reduce cost and effort | perfrom redesign and modifcation work in Igiugig as needed with local fabrication resources. If assembly slips past August 2018 deploy system in June 2019
2017-02-24 | Technical | 1.7 System reliability | Power System /comissioning issues | 7 | 7 | Assembly and commissioning | M. Worthington (Project Management) | - | Q | 5 | 3 | 15 | Power System deployment/comissioning encounters unexpected difficulties | mitigate | prior device testing and component testing in Nikiksi and elsewhere will reduce unexpected issues with deployment or comissioning. Thewe validation steps completed by May 2018 | August | 5 | 2 | 10 | Per shipment validation work in Nikiksi with device and with other components in lab will recude likelihood of unexpcted issues | testing may cause damge to components, increased cost and effort | Test all components in configuration for Igiugig deployment when practical and within budget | Resolove issues with locally available resources. If issue not resolved by the end of Septmber 2018, remove device for modifcation/repair and redeploy in June 2019
2017-02-24 | Technical | 1.7 System reliability | Complications with winter ice | 6 | 6 | Extreme events | R. Tyler (lead engineer) | - | Q | 5 | 4 | 20 | Ice accumlation on or interaction with device causes power disruption, reduction, or equipment damage | mitigate | Collection of in river ice data for 2 years prior to deployment feeds engineeering and IO&M planning, June 2017- June 2018. ON device ice monitoring allows for operational state modification if adverse conditions or interactions occure | June | 5 | 3 | 15 | Uncertiainty of ice interaction or in river formation leads to impact on device operations | Increased cost and effort | perform thorough analysis of ice data from in river data collection, perform thorough FMEA of risks this type of ice formation or movement will have on device | Remove divce from irver if possible, or curtail or disccontinue device operations until ice event passes or equipment can be safely removed and repaired if damaged
2017-02-24 | External | 4.4 Environmental/weather | Adverse salmon smolt interactions | 6 | 6 | Normal power production | N. Johnson (environmental) | - | E | 4 | 4 | 16 | Salmon smolt data collection shows adverse reaction, or inadequate data collection does not provide regualtory agencies with adequate information to allow operation or testing during salmon smolt outmigration | mitigate | Develop rigorous fish monitroing pland in budget period 2. Consulst with state and federal agencies reularly to ensure study plan and instrumentation provides adeqaute infoarmaton for decision making, operate device only under continuoius montiroring during smolt outmigration | May | 4 | 3 | 12 | Lack of established industry standard for smolt monitoring ore previous data on MHK device with salmon smolt means effort will be experimental in nature, and any result or lack of is possible | incresed cost without eliminating or adequtely redugin risk | Establish adaptive management plan with agencies in advance of deployment to allow real time data anlaysis and modifcaiton of device operational plan if adverse interactions occur | Stop device operations during smolt outmigration, remove device if necessary
2017-02-24 | Technical | 1.7 System reliability | Device removal complications | 7 | 7 | Decommissioning | M. Worthington (Project Management) | - | Q | 5 | 3 | 15 | Device removal complicated by technological or environmental factors | mitigate | Buoyancy system includes redundant and isoalted retrieval mechanisms, pre testing In Nikiski to reduce risk of retreival issues arrising | May | 5 | 2 | 10 | redundant pretested systems reduce likleihood of retrieval issue | increased cost and effort, increase system complexity | Document results of pre testing in Nikiksi, visually inspect devid during deployment with attention to buoyancy system components | Utilize locaaly available resources to develop contingency retrival operations
2017-02-24 | Commercial | 3.3 Suppliers and vendors | Higher cost for maintenance and logistical support required | 7 | 6 | Normal power production | M. Worthington (Project Management) | - | C | 4 | 4 | 16 | Higher cost for maintenance and logistical support required for final design and operations plan, including training and personnel requirements, external equipment and spares. | mitigate | Developing system requirements will be critical for determining technical scope for operations and maintenance technical support; involve local resources and include 3rd party input to accurately ascertain feasibility of proposed systems for logistical and technical requirements in remote environment. Develop trained leads during project who will be responsible for operating the systems after the project. | before assembly and commissioning | 2 | 2 | 4 | Higher cost risk should be lessened | complex supply chain and remote area logistics may still impact cost estimates | structure contract to include incentives/penalties and FFP where possible | follow contractual provisions for higher costs, ensure lessons learned have path for improvement post-process
2017-02-24 | [11 empty] | 0 | [6 empty] | 0
2017-02-24 | [11 empty] | 0 | [6 empty] | 0
2017-02-24 | [11 empty] | 0 | [6 empty] | 0
2017-02-24 | [11 empty] | 0 | [6 empty] | 0
2017-02-24 | [11 empty] | 0 | [6 empty] | 0
2017-02-24 | [11 empty] | 0 | [6 empty] | 0
2017-02-24 | [11 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0
[12 empty] | 0 | [6 empty] | 0

## Valid data fields
Important Note: use the following procedure to add/or change valid data fields for this risk register
1) add new data option below appropriate column within "Valid data field" worksheet
2) click (Ctrl+F3), for Name Manager window
3) highlight Name being modified, click "Edit" icon
4) under "Refers to:", extend range to include new data
5) click "OK" icon
6) click "Close" icon
7) new data should now appear as option within "Risk Register" worksheet
RBS | Technical | Management | Commercial | External | TRL | TPL | Life | Owner | + or - | Type | Severity | Frequency | NegResponse | PosResponse | Timing
Technical | 1.1 Scope definition | 2.1 Project management | 3.1 Contractual terms and conditions | 4.1 Legislation | NA | NA | NA | R. Tyler (lead engineer) | - | S | 0 | 0 | avoid | exploit | now
Management | 1.2 Requirements definition | 2.2 Program/Portfolio management | 3.2 Internal procurement | 4.2 Exchange rates | All | All | Multiple (or all) life phases | N. Johnson (environmental) | + | C | 1 | 1 | transfer | share | before specification
Commercial | 1.3 Estimates, assumptions, constraints | 2.3 Operations management | 3.3 Suppliers and vendors | 4.3 Site/facilities | 1 | 1 | Specification | M. Worthington (Project Management) |  | T | 2 | 2 | mitigate | enhance | before design finalized
External | 1.4 Technical processes | 2.4 Organization | 3.4 Subcontracts | 4.4 Environmental/weather | 2 | 2 | Design | A. Salmon (PI) |  | P | 3 | 3 | accept | accept | before PO issued
| 1.5 Technology | 2.5 Human resourcing | 3.5 Client/customer stability | 4.5 Competition | 3 | 3 | Manufacturing | J. McEntee (CTO) |  | Q | 4 | 4 |  |  | before manufacturing
| 1.6 Technical interfaces | 2.6 Funding | 3.6 Partnerships and joint ventures | 4.6 Regulatory | 4 | 4 | Transportation | C. Marnagh (Engineering mgmt) |  | E | 5 | 5 |  |  | before assembly and commissioning
| 1.7 System reliability | 2.7 Communication | 3.7 LCOE | 4.7 Political | 5 | 5 | Assembly and commissioning | J. Kasper (UAA lead) |  | R |  |  |  |  | before decommissioning
| 1.8 Performance | 2.8 Information |  | 4.8 Force majeure | 6 | 6 | Normal power production | [7 empty] | January
| 1.9 Safety | 2.9 Quality |  | 4.9 External stakeholder | 7 | 7 | Extreme events | [7 empty] | February
| 1.10 Security | 2.10 Reputation |  |  | 8 | 8 | Faults | [7 empty] | March
[5 empty] | 9 | 9 | Maintenance | [7 empty] | April
[7 empty] | Repair | [7 empty] | May
[7 empty] | Decommissioning | [7 empty] | June
July
August
September
October
November
December